## Summary
Tester: | Neeraja Maddala |  | Last Update: | 2021-08-23 |  |  | Last Review By:
FAIL | 2 | Open Defects | 3
PASS | 8 | Closed Defects | 0
NOT RUN | 17 | Total | 3
BLOCK | 0
NOT APPLICABLE | 0
Total | 27
ACC Matrix
Components |  |  | Attributes | [5 empty] | General
Sprint | Feature | Story | Secure | Compliance | Auditable | Reliable | Accessible | Responsive | Status | Comments
Sprint1 | Landing Page | Navigate URL | 0 | 1 | 0 | 0 | 0 | 0 | Done
Sprint1 | Page Header | iSelect button | 0 | 1 | 3 | 0 | 0 | 0 | In Progress
Sprint1 | Page Header | Car Insurance Text | 0 | 1 | 0 | 0 | 0 | 0 | In Progress
Sprint1 | Page Header | Our Services | 0 | 1 | 0 | 0 | 0 | 0 | In Progress
Sprint1 | Page Header | Help | 0 | 1 | 0 | 0 | 0 | 0 | In Progress
Sprint1 | Form Header | Form heading,Progress Bar, Back Button, Help Text for Next,Help text for form | 0 | 0 | 0 | 0 | 0 | 0 | Done
Sprint1 | Find Your car | Make | 1 | 1 | 3 | 0 | 1 | 3 | In Progress
Sprint1 | Find Your car | Model | 1 | 1 | 3 | 0 | 1 | 3 | Done
Sprint1 | Find Your car | Year | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint1 | Find Your car | Colour | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Find Your car | Car Type or series | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Find Your car | Transmission | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Find Your car | Fuel Type | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Footer | Footer Help Text | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Footer | Footer Images | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Footer | Phone Number | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Footer | Opening Hours | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
Sprint2 | Footer | Important Information | 0 | 0 | 0 | 0 | 0 | 0 | Not Started

## Scenarios
Component | Attribute | Capability | Scenario | Comments | Status
Navigate URL | Compliance | Navigate URL Is Compliance | Scenario :When User enters the URL "https://car.iselect.com.au/car/compare-car-insurance/gatewayStore" Then User should navigate to car Insurance Home Page" |  | PASS
iSelect button | Compliance | iSelect button Is Compliance | Scenario:When User clicks on iSelect button Then User should be able to navigate to "https://www.iselect.com.au/" | Background:Given user Navigate to URL ""https://car.iselect.com.au/car/compare-car-insurance/gatewayStore" | PASS
iSelect button | Auditable | iSelect button Is Auditable | When User's iSelect button interactions are recorded using analytics |  | NOT RUN
iSelect button | Auditable | iSelect button Is Auditable | When User's iSelect errors are recorded in error logs |  | NOT RUN
iSelect button | Auditable | iSelect button Is Auditable | When User's iSelect errors are recorded in audit logs |  | NOT RUN
Car Insurance Text | Compliance | Car Insurance Text Is Compliance | Then User should see the "Car Insurance" help text is displayed |  | PASS
Our Services | Compliance | Our Services Is Compliance | When User clicks on our services link Then user should see below options and also navigate to corresponding page Under "Insurance" Section Health,Car,Life,Income&Protection,Home&Contents,Business,Travel,Pet ,OverseasHealthCover |  | PASS
Our Services | Compliance | Our Services Is Compliance | When User clicks on our services link Then user should see below options and also navigate to corresponding page Under" Utilities & Finance" Section Electricty&Gas,Internet,Home Loans,Mobile Phones,Moving House |  | PASS
Help | Compliance | Help Is Compliance | Then User should see the "Help" help text is displayed And Help Should display after click on Help |  | PASS
Make | Compliance | Make Is Compliance | When User Enters "Mazda" in Make Drop down Then "Mazda" should display in drop down | It is showing 2 "Mazda" values | FAIL
Make | Auditable | Make Is Auditable | When User's Make drop down interactions are recorded using analytics |  | NOT RUN
Make | Auditable | Make Is Auditable | When User's Make drop down errors are recorded in error logs |  | NOT RUN
Make | Auditable | Make Is Auditable | When User's Make drop down errors are recorded in audit logs |  | NOT RUN
Make | Secure | Make Is Secure | When User Enter any Special characters Then Make drop down should not display any value | Negative Test case | PASS
Make | Responsive | Make Is Responsive | When User can access Make Drop Down component on mobile device screen |  | NOT RUN
Make | Responsive | Make Is Responsive | When User can access Make Drop Down component on tablet/ipad device screen |  | NOT RUN
Make | Responsive | Make Is Responsive | When User can access Make Drop Down component on laptop device screen |  | NOT RUN
Make | Accessible | Make Is Accessible | When All the elements on the page including Make drop is readable |  | NOT RUN
Model | Compliance | Model Is Compliance | When User Enters "Mazda" in Make Drop down And User Enter "Demio " in Model Drop down Then "Demio" should display in drop down | It is not showing "Demio" value | FAIL
Model | Auditable | Model Is Auditable | When User's Model drop down interactions are recorded using analytics |  | NOT RUN
Model | Auditable | Model Is Auditable | When User's Model drop down errors are recorded in error logs |  | NOT RUN
Model | Auditable | Model Is Auditable | When User's Mode, drop down errors are recorded in audit logs |  | NOT RUN
Model | Secure | Model Is Secure | When User Enter any Special characters Then Model drop down should not display any value | Negative Test case | PASS
Model | Responsive | Model Is Responsive | When User can access Make Drop Down component on mobile device screen |  | NOT RUN
Model | Responsive | Model Is Responsive | When User can access Model Drop Down component on tablet/ipad device screen |  | NOT RUN
Model | Responsive | Model Is Responsive | When User can access Model Drop Down component on laptop device screen |  | NOT RUN
Model | Accessible | Model Is Accessible | When All the elements on the page including Model drop is readable |  | NOT RUN

## Defects
Defect # | Story/Component | Title | Steps | Tags | Status | Priority | Actions
D001 | Make | Make drop down is not showing correct values | 1. Navigate into https://car.iselect.com.au/car/compare-car-insurance/gatewayStore 2.User enters "Mazda" value in make drop down Then dop down is displaying 2 values instead of 1 value .Ui is not deleted cookies after borwser refersh or after browser close | UI,Dev,Functional,Web,Sprint1 | Open | Medium
D002 | Make | Model is not displaying "Demio" for make "Mazda" | 1. Navigate into https://car.iselect.com.au/car/compare-car-insurance/gatewayStore 2.User Select "Mazda" value in make drop down 3.User trying to Enter "Demio" Model But, UI is not showing Demio Model | UI,Dev,Functional,Web,Sprint1 | Open | High
D003 | Level of Cover | Third party property images icon are not working | 1. Navigate into https://car.iselect.com.au/car/compare-car-insurance/gatewayStore 2.User Select the image of Third Party Property images Then nothing is happening on click on images | UI,Dev,Functional,Web,Sprint1 | Open | High